## Jira_Details
Sl No. | PBI Number | Issue Type | Sprint | Status | Labels | Feature | Priority | Summary | TCs Identified | TCs Coded | Reporter | Assignee | Estimated Time | Remaining TIme | Time Spent
1 | RC18-100 | Bug | Sprint 1 | Open | NA | NA | Medium | Bug in Feature-3 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
2 | RC18-99 | Bug | Sprint 1 | Open | NA | NA | High | Bug in Feature-2 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
3 | RC18-98 | Bug | Sprint 1 | Open | NA | NA | Low | Bug in Feature-5 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
4 | RC18-97 | Bug | Sprint 1 | Open | NA | NA | Highest | Crash of server on Feature-6 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
5 | RC18-96 | Bug | Sprint 0 | Open | NA | NA | Medium | Bug in Feature-4 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
6 | RC18-95 | Bug | Sprint 0 | Open | NA | NA | Lowest | Bug in Feature-5 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
7 | RC18-94 | Bug | Sprint 0 | Open | NA | NA | Medium | Bug in Feature-3 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
8 | RC18-93 | Bug | Sprint 0 | Open | NA | NA | Low | Bug in Feature-2 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
9 | RC18-92 | Bug | Sprint 0 | Open | NA | NA | Medium | json payload format is not supported on Feature-1 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
10 | RC18-91 | Bug | Sprint 0 | Open | NA | NA | Highest | Compilation Issue on Feature-1 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
11 | RC18-90 | Bug | Sprint 0 | Open | NA | NA | Highest | Crash of server on Feature-1 | NA | NA | Dinesh Rajendran | None | 0 | 0 | 0
12 | RC18-89 | Story | Sprint 2 | In Progress | TC | Feature-5 | Highest | Commercialization requires test case coding for Feature-5 validation : Phase3 | NA | 7.0 | Dinesh Rajendran | Laxmi Sogani | 24 | 24 | 0
13 | RC18-88 | Story | Sprint 2 | In Progress | TP | Feature-5 | Highest | Commercialization requires test case identification for Feature-5 validation : Phase3 | 10.0 | NA | Dinesh Rajendran | Laxmi Sogani | 8 | 4 | 4
14 | RC18-87 | Story | Sprint 2 | Resolved | CC | Feature-6 | Highest | Commercialization requires framework enhancements for Feature-6 validation : Phase3 | NA | NA | Dinesh Rajendran | Shubham Prajapati | 16 | 8 | 8
15 | RC18-86 | Story | Sprint 2 | In Progress | TC | Feature-6 | Highest | Commercialization requires test case coding for Feature-6 validation : Phase3 | NA | 7.0 | Dinesh Rajendran | Shubham Prajapati | 8 | 0 | 8
16 | RC18-85 | Story | Sprint 2 | In Progress | CC | Feature-3 | Highest | Commercialization requires framework enhancements for Feature-3 validation : Phase3 | NA | NA | Dinesh Rajendran | Shivam Seth | 8 | 2 | 6
17 | RC18-84 | Story | Sprint 2 | Resolved | TC | Feature-3 | Highest | Commercialization requires test case coding for Feature-3 validation : Phase3 | NA | 6.0 | Dinesh Rajendran | Shivam Seth | 16 | 16 | 0
18 | RC18-83 | Story | Sprint 2 | Resolved | TP | Feature-3 | Highest | Commercialization requires test case identification for Feature-3 validation : Phase3 | 8.0 | NA | Dinesh Rajendran | Shivam Seth | 8 | 0 | 8
19 | RC18-82 | Story | Sprint 2 | Open | TC | Feature-6 | Highest | Commercialization requires test case coding for Feature-6 validation : Phase2 | NA | NA | Dinesh Rajendran | Kushal Shah | 24 | 24 | 0
20 | RC18-81 | Story | Sprint 2 | Resolved | TP | Feature-6 | Highest | Commercialization requires framework enhancements for Feature-6 validation : Phase2 | NA | NA | Dinesh Rajendran | Kushal Shah | 8 | 0 | 8
21 | RC18-80 | Story | Sprint 2 | Open | RA | NA | Medium | Release Activity-6 | NA | NA | Dinesh Rajendran | Laxmi Sogani | 4 | 4 | 0
22 | RC18-79 | Story | Sprint 2 | Open | RA | NA | Medium | Release Activity-5 | NA | NA | Dinesh Rajendran | Shubham Prajapati | 4 | 4 | 0
23 | RC18-78 | Story | Sprint 2 | Open | RA | NA | Medium | Release Activity-4 | NA | NA | Dinesh Rajendran | Shivam Seth | 4 | 4 | 0
24 | RC18-77 | Story | Sprint 2 | Open | RA | NA | Medium | Release Activity-3 | NA | NA | Dinesh Rajendran | Kushal Shah | 4 | 4 | 0
25 | RC18-76 | Story | Sprint 2 | Resolved | SP | NA | Medium | Sprint Planning-6 | NA | NA | Dinesh Rajendran | Laxmi Sogani | 4 | 0 | 4
26 | RC18-75 | Story | Sprint 2 | Resolved | SP | NA | Medium | Sprint Planning-5 | NA | NA | Dinesh Rajendran | Shubham Prajapati | 4 | 0 | 4
27 | RC18-74 | Story | Sprint 2 | Resolved | SP | NA | Medium | Sprint Planning-4 | NA | NA | Dinesh Rajendran | Shivam Seth | 4 | 0 | 4
28 | RC18-73 | Story | Sprint 2 | Resolved | SP | NA | Medium | Sprint Planning-3 | NA | NA | Dinesh Rajendran | Kushal Shah | 4 | 0 | 4
29 | RC18-72 | Story | Sprint 2 | Resolved | SP | NA | Medium | Sprint Planning-2 | NA | NA | Dinesh Rajendran | Abdulla Khan Pathan | 4 | 0 | 4
30 | RC18-71 | Story | Sprint 2 | In Progress | TC | Feature-4 | High | Commercialization requires test case coding for Feature-4 validation : Phase3 | NA | 7.0 | Dinesh Rajendran | Abdulla Khan Pathan | 20 | 20 | 0
31 | RC18-70 | Story | Sprint 2 | In Progress | TC | Feature-4 | High | Commercialization requires test case coding for Feature-4 validation : Phase2 | NA | 5.0 | Dinesh Rajendran | Dinesh Rajendran | 16 | 8 | 8
32 | RC18-69 | Story | Sprint 2 | In Progress | TP | Feature-4 | High | Commercialization requires test case identification for Feature-4 validation : Phase2 | 12.0 | NA | Dinesh Rajendran | Dinesh Rajendran | 8 | 0 | 8
33 | RC18-68 | Story | Sprint 2 | Open | RA | NA | Medium | Release Activity-1 | NA | NA | Dinesh Rajendran | Dinesh Rajendran | 4 | 4 | 0
34 | RC18-67 | Story | Sprint 2 | Resolved | SP | NA | Medium | Sprint Planning-1 | NA | NA | Dinesh Rajendran | Dinesh Rajendran | 4 | 0 | 4
35 | RC18-66 | Story | Sprint 1 | Resolved | CC | Feature-5 | High | Commercialization requires framework enhancements for Feature-5 validation : Phase2 | NA | NA | Dinesh Rajendran | Laxmi Sogani | 8 | 4 | 4
36 | RC18-65 | Story | Sprint 1 | Resolved | TC | Feature-5 | High | Commercialization requires test case coding for Feature-5 validation : Phase2 | NA | 5.0 | Dinesh Rajendran | Laxmi Sogani | 24 | 16 | 8
37 | RC18-64 | Story | Sprint 1 | Resolved | RA | NA | Medium | Release Activity-6 | NA | NA | Dinesh Rajendran | Laxmi Sogani | 4 | 0 | 8
38 | RC18-63 | Story | Sprint 1 | Resolved | SP | NA | Medium | Sprint Planning-6 | NA | NA | Dinesh Rajendran | Laxmi Sogani | 4 | 0 | 4
39 | RC18-62 | Story | Sprint 1 | Resolved | RA | NA | Medium | Release Activity-5 | NA | NA | Dinesh Rajendran | Shubham Prajapati | 4 | 4 | 0
40 | RC18-61 | Story | Sprint 1 | Resolved | CC | Feature-6 | Highest | Commercialization requires framework enhancements for Feature-6 validation : Phase1 | NA | NA | Dinesh Rajendran | Shubham Prajapati | 8 | 0 | 8
41 | RC18-60 | Story | Sprint 1 | Resolved | TC | Feature-6 | Highest | Commercialization requires test case coding for Feature-6 validation : Phase1 | NA | 5.0 | Dinesh Rajendran | Shubham Prajapati | 16 | 16 | 0
42 | RC18-59 | Story | Sprint 1 | Resolved | TP | Feature-6 | Highest | Commercialization requires test case identification for Feature-6 validation : Phase1 | 5.0 | NA | Dinesh Rajendran | Shubham Prajapati | 8 | 8 | 0
43 | RC18-58 | Story | Sprint 1 | Resolved | SP | NA | Medium | Sprint Planning-5 | NA | NA | Dinesh Rajendran | Shubham Prajapati | 4 | 0 | 8
44 | RC18-57 | Story | NA | Closed | RA | NA | Medium | Release Activity-4 | NA | NA | Dinesh Rajendran | Shivam Seth | 4 | 0 | 4
45 | RC18-56 | Story | Sprint 1 | Resolved | CC | Feature-3 | Highest | Commercialization requires framework enhancements for Feature-3 validation : Phase2 | NA | NA | Dinesh Rajendran | Shivam Seth | 8 | 4 | 4
46 | RC18-55 | Story | Sprint 1 | Resolved | TC | Feature-3 | Highest | Commercialization requires test case coding for Feature-3 validation : Phase2 | NA | 6.0 | Dinesh Rajendran | Shivam Seth | 16 | 12 | 4
47 | RC18-54 | Story | Sprint 1 | Resolved | TP | Feature-3 | Highest | Commercialization requires test case identification for Feature-3 validation : Phase2 | 7.0 | NA | Dinesh Rajendran | Shivam Seth | 8 | 4 | 4
48 | RC18-53 | Story | Sprint 1 | Resolved | SP | NA | Medium | Sprint Planning-4 | NA | NA | Dinesh Rajendran | Shivam Seth | 4 | 0 | 4
49 | RC18-52 | Story | Sprint 1 | Resolved | RA | NA | Medium | Release Activity-3 | NA | NA | Dinesh Rajendran | Kushal Shah | 4 | 0 | 8
50 | RC18-51 | Story | Sprint 1 | Resolved | CC | Feature-2 | High | Commercialization requires framework enhancements for Feature-2 validation : Phase2 | NA | NA | Dinesh Rajendran | Kushal Shah | 8 | 0 | 8
51 | RC18-50 | Story | Sprint 1 | Resolved | TC | Feature-2 | High | Commercialization requires test case coding for Feature-2 validation : Phase2 | NA | 4.0 | Abdulla Khan Pathan | Kushal Shah | 16 | 4 | 12
52 | RC18-49 | Story | Sprint 1 | Resolved | TP | Feature-2 | High | Commercialization requires test case identification for Feature-2 validation : Phase2 | 10.0 | NA | Abdulla Khan Pathan | Kushal Shah | 8 | 0 | 8
53 | RC18-48 | Story | Sprint 1 | Resolved | SP | NA | Medium | Sprint Planning-3 | NA | NA | Abdulla Khan Pathan | Kushal Shah | 4 | 0 | 12
54 | RC18-47 | Story | Sprint 1 | Resolved | RA | NA | Medium | Release Activity-1 | NA | NA | Abdulla Khan Pathan | Abdulla Khan Pathan | 4 | 0 | 4
55 | RC18-46 | Story | NA | Closed | CC | Feature-1 | High | Commercialization requires framework enhancements for Feature-1 validation : Phase3 | NA | NA | Abdulla Khan Pathan | Abdulla Khan Pathan | 8 | 0 | 8
56 | RC18-45 | Story | Sprint 1 | Resolved | TC | Feature-1 | High | Commercialization requires test case coding for Feature-1 validation : Phase3 | NA | 7.0 | Abdulla Khan Pathan | Abdulla Khan Pathan | 16 | 0 | 16
57 | RC18-44 | Story | Sprint 1 | Resolved | TP | Feature-1 | High | Commercialization requires test case identification for Feature-1 validation : Phase3 | 7.0 | NA | Abdulla Khan Pathan | Abdulla Khan Pathan | 8 | 0 | 12
58 | RC18-43 | Story | NA | Closed | SP | NA | Medium | Sprint Planning-2 | NA | NA | Abdulla Khan Pathan | Abdulla Khan Pathan | 4 | 4 | 0
59 | RC18-42 | Story | Sprint 1 | Resolved | RA | NA | Medium | Release Activity-1 | NA | NA | Abdulla Khan Pathan | Dinesh Rajendran | 4 | 0 | 16
60 | RC18-41 | Story | Sprint 1 | Resolved | CC | Feature-1 | Highest | Commercialization requires framework enhancements for Feature-1 validation : Phase2 | NA | NA | Abdulla Khan Pathan | Dinesh Rajendran | 8 | 0 | 8
61 | RC18-40 | Story | Sprint 1 | Resolved | TC | Feature-1 | Highest | Commercialization requires test case coding for Feature-1 validation : Phase2 | NA | 3.0 | Abdulla Khan Pathan | Dinesh Rajendran | 16 | 0 | 16
62 | RC18-39 | Story | Sprint 1 | Resolved | TP | Feature-1 | Highest | Commercialization requires test case identification for Feature-1 validation : Phase2 | NA | NA | Abdulla Khan Pathan | Dinesh Rajendran | 8 | 0 | 8
63 | RC18-38 | Story | Sprint 1 | Resolved | SP | NA | Medium | Sprint Planning-1 | NA | NA | Abdulla Khan Pathan | Dinesh Rajendran | 4 | 0 | 8
64 | RC18-37 | Story | Sprint 0 | Resolved | RA | NA | High | Release Activity-6 | NA | NA | Abdulla Khan Pathan | Shubham Prajapati | 4 | 0 | 4
65 | RC18-36 | Story | Sprint 0 | Resolved | CC | Feature-5 | High | Commercialization requires framework enhancements for Feature-5 validation : Phase1 | NA | NA | Abdulla Khan Pathan | Shubham Prajapati | 8 | 0 | 8
66 | RC18-35 | Story | Sprint 0 | Resolved | TC | Feature-5 | High | Commercialization requires test case coding for Feature-5 validation : Phase1 | NA | 8.0 | Abdulla Khan Pathan | Shubham Prajapati | 8 | 0 | 8
67 | RC18-34 | Story | Sprint 0 | Resolved | TP | Feature-5 | High | Commercialization requires test case identification for Feature-5 validation : Phase1 | 5.0 | NA | Abdulla Khan Pathan | Shubham Prajapati | 16 | 9 | 7
68 | RC18-33 | Story | Sprint 0 | Resolved | SP | NA | High | Sprint Planning-6 | NA | NA | Abdulla Khan Pathan | Shubham Prajapati | 4 | 0 | 8
69 | RC18-32 | Story | Sprint 0 | Resolved | RA | NA | High | Release Activity-5 | NA | NA | Abdulla Khan Pathan | Shivam Seth | 4 | 0 | 6
70 | RC18-31 | Story | Sprint 0 | Resolved | CC | Feature-4 | High | Commercialization requires framework enhancements for Feature-4 validation : Phase1 | NA | NA | Abdulla Khan Pathan | Shivam Seth | 16 | 0 | 16
71 | RC18-30 | Story | Sprint 0 | Resolved | TP | Feature-4 | High | Commercialization requires test case identification for Feature-4 validation : Phase1 | 8.0 | NA | Abdulla Khan Pathan | Shivam Seth | 16 | 0 | 16
72 | RC18-29 | Story | Sprint 0 | Resolved | SP | NA | High | Sprint Planning-5 | NA | NA | Abdulla Khan Pathan | Shivam Seth | 4 | 0 | 6
73 | RC18-28 | Story | Sprint 0 | Resolved | RA | NA | High | Release Activity-4 | NA | NA | Abdulla Khan Pathan | Laxmi Sogani | 4 | 4 | 0
74 | RC18-27 | Story | Sprint 0 | Resolved | CC | Feature-3 | High | Commercialization requires framework enhancements for Feature-3 validation : Phase1 | NA | NA | Abdulla Khan Pathan | Laxmi Sogani | 8 | 8 | 0
75 | RC18-26 | Story | Sprint 0 | Resolved | TC | Feature-3 | High | Commercialization requires test case coding for Feature-3 validation : Phase1 | NA | 10.0 | Abdulla Khan Pathan | Laxmi Sogani | 16 | 8 | 8
76 | RC18-25 | Story | Sprint 0 | Resolved | TP | Feature-3 | High | Commercialization requires test case identification for Feature-3 validation : Phase1 | NA | NA | Abdulla Khan Pathan | Laxmi Sogani | 8 | 0 | 8
77 | RC18-24 | Story | Sprint 0 | Resolved | SP | NA | High | Sprint Planning-4 | NA | NA | Abdulla Khan Pathan | Laxmi Sogani | 4 | 0 | 8
78 | RC18-23 | Story | Sprint 0 | Resolved | TC | Feature-2 | Highest | Commercialization requires test case coding for Feature-2 validation : Phase2 | NA | 9.0 | Abdulla Khan Pathan | Kushal Shah | 20 | 20 | 0
79 | RC18-22 | Story | Sprint 0 | Resolved | SP | NA | Highest | Sprint Planning-3 | NA | NA | Abdulla Khan Pathan | Kushal Shah | 4 | 0 | 8
80 | RC18-21 | Story | Sprint 0 | Resolved | TP | Feature-2 | Highest | Commercialization requires test case identification for Feature-2 validation : Phase1 | 7.0 | NA | Abdulla Khan Pathan | Dinesh Rajendran | 8 | 0 | 8
81 | RC18-20 | Story | Sprint 0 | Resolved | RA | NA | Highest | Release Activity-2 | NA | NA | Abdulla Khan Pathan | Dinesh Rajendran | 4 | 0 | 4
82 | RC18-19 | Story | Sprint 0 | Resolved | SP | NA | Highest | Sprint Planning-2 | NA | NA | Abdulla Khan Pathan | Dinesh Rajendran | 4 | 0 | 4
83 | RC18-18 | Story | Sprint 0 | Resolved | CC | Feature-2 | Highest | Commercialization requires framework enhancements for Feature-2 validation : Phase1 | NA | NA | Abdulla Khan Pathan | Dinesh Rajendran | 16 | 8 | 8
84 | RC18-17 | Story | Sprint 0 | Resolved | RA | NA | Highest | Release Activity-1 | NA | NA | Abdulla Khan Pathan | Abdulla Khan Pathan | 4 | 0 | 8
85 | RC18-16 | Story | Sprint 0 | Resolved | CC | Feature-1 | Highest | Commercialization requires framework enhancements for Feature-1 validation : Phase1 | NA | NA | Abdulla Khan Pathan | Abdulla Khan Pathan | 8 | 0 | 8
86 | RC18-15 | Story | Sprint 0 | Resolved | TC | Feature-1 | Highest | Commercialization requires test case coding for Feature-1 validation : Phase1 | NA | 4.0 | Abdulla Khan Pathan | Abdulla Khan Pathan | 16 | 16 | 0
87 | RC18-14 | Story | Sprint 0 | Resolved | SP | NA | Highest | Sprint Planning-1 | NA | NA | Abdulla Khan Pathan | Abdulla Khan Pathan | 4 | 0 | 4
88 | RC18-13 | Story | Sprint 0 | Resolved | TP | Feature-1 | Highest | Commercialization requires test case identification for Feature-1 validation | 12.0 | NA | Abdulla Khan Pathan | Abdulla Khan Pathan | 8 | 8 | 0
89 | RC18-12 | Epic | NA | Open | NA | NA | Medium | Testing of Feature-6 | NA | NA | Abdulla Khan Pathan | None | 0 | 0 | 0
90 | RC18-11 | Epic | NA | Open | NA | NA | Highest | Testing of Feature-5 | NA | NA | Abdulla Khan Pathan | None | 0 | 0 | 0
91 | RC18-10 | Epic | NA | Open | NA | NA | Medium | Testing of Feature-4 | NA | NA | Abdulla Khan Pathan | None | 0 | 0 | 0
92 | RC18-9 | Epic | NA | Open | NA | NA | Medium | Testing of Feature-3 | NA | NA | Abdulla Khan Pathan | None | 0 | 0 | 0
93 | RC18-8 | Epic | NA | Open | NA | NA | Highest | Testing of Feature-2 | NA | NA | Abdulla Khan Pathan | None | 0 | 0 | 0
94 | RC18-7 | Epic | NA | Open | NA | NA | Highest | Testing of Feature-1 | NA | NA | Abdulla Khan Pathan | None | 0 | 0 | 0